## Sheet1
TEAM NUMBER | 28
PROJECT NAME | Fleet Management
PROJECT MENTOR (sponsor) | Akhil
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Time Calculation Error
Week 1 (January 16 - January 21)
GIT Repository setup | Preparation | Aryanil | 1 | 0.5 | Done | 0.5
Client meeting | Coordination | Aviral | 5 | 4 | Done | 1
Research existing technology | Preparation | Sherley | 3 | 5 | Done | -2
Team Meeting | Coordination | Aviral | 5 | 4 | Done | 1
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5
Week 2 (January 22 - January 28)
Project Synopsis Writeup | Documentation | Sherley | 3 | 3.5 | Done | -0.5
Project Plan Document | Documentation | Akshitha | 4 | 4.5 | Done | -0.5
Software Requirement Specification | Documentation | Aviral | 3 | 2.5 | Done | 0.5
Team Meeting | Coordination | Aviral | 5 | 7 | Done | -2
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5