## Sheet1
TEAM NUMBER | 28
PROJECT NAME | Fleet Management
PROJECT MENTOR (sponsor) | Akhil
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Time Calculation Error
Week 1 (January 16 - January 21)
GIT Repository setup | Preparation | Aryanil | 1 | 0.5 | Done
Client meeting | Coordination | Aviral | 5 | 4 | Done
Research existing technology | Preparation | Sherley | 3 | 5 | Done
Team Meeting | Coordination | Aviral | 5 | 4 | Done
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done
Status tracker | Documentation | Satvik | 1 | 0.5 | Done
Week 2 (January 22 - January 28)
Project Synopsis Writeup | Documentation | Sherley | 3 | 3.5 | Done
Project Plan Document | Documentation | Akshitha | 4 | 4.5 | Done
Software Requirement Specification | Documentation | Aviral | 3 | 2.5 | Done
Team Meeting | Coordination | Aviral | 5 | 7 | Done
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done
Status tracker | Documentation | Satvik | 1 | 0.5 | Done
Week 3 (January 29 - February 4)
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done
Reasearch TSP Algorithm for Routing | Preparation | Aryanil | 1 | 1 | Done
VROOM | Preparation | Aryanil | 2 | 2 | Done
Team Meeting | Coordination | Aviral | 7.5 | 7.5 | Done
Update Status Tracker | Documentation | Satvik | 2 | 0.5 | Done