## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 28
PROJECT NAME | Fleet Management
PROJECT MENTOR (sponsor) | Akhil
TEAM MEMBERS | Akshitha
Aryanil
Aviral
Satvik
Sherley

## Status
TEAM NUMBER | 28
PROJECT NAME | Fleet Management
PROJECT MENTOR (sponsor) | Akhil
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Time Calculation Error
Week 1 (January 16 - January 21)
GIT Repository setup | Preparation | Aryanil | 1 | 0.5 | Done | 0.5
Client meeting | Coordination | Aviral | 5 | 4 | Done | 1
Research existing technology | Preparation | Sherley | 3 | 5 | Done | -2
Team Meeting | Coordination | Aviral | 5 | 4 | Done | 1
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5
Week 2 (January 22 - January 28)
Project Synopsis Writeup | Documentation | Sherley | 3 | 3.5 | Done | -0.5
Project Plan Document | Documentation | Akshitha | 4 | 4.5 | Done | -0.5
Software Requirement Specification | Documentation | Aviral | 3 | 2.5 | Done | 0.5
Team Meeting | Coordination | Aviral | 5 | 7 | Done | -2
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5
Week 3 (January 29 - February 4)
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Research TSP Algorithm for Routing | Preparation | Aryanil | 1 | 1 | Done | 0
VROOM | Preparation | Aryanil | 2 | 2 | Done | 0
Team Meeting | Coordination | Aviral | 7.5 | 7.5 | Done | 0
Update Status Tracker | Documentation | Satvik | 2 | 0.5 | Done | 1.5
Week 4 (February 5 - February 11)
Reasearch Grasshopper Optimisation Technique | Preparation | Aviral | 2 | 3 | Done | -1
Research on Data Acquisition | Preparation | Sherley | 3 | 3.5 | Done | -0.5
Data Importing Techniques | Preparation | Sherley | 2.5 |  | Planned | 2.5
Research Heuristics Algorithms | Preparation | Aviral | 3 | 2.5 | Done | 0.5
Research on Geocoding | Preparation | Akshitha | 2 | 1.5 | Done | 0.5
Research on TSP (Contd.) | Preparation | Aryanil | 2 | 1 | Delayed | 1
Research on PgRouting | Preparation | Satvik | 2 |  | Done
Update Status Tracker | Documentation | Satvik | 0.5 | 0.5 | Done | 0
Week 5 (February 12 - February 18)
Update SRS to match format | Documentation | Aviral | 5 | 7 | Done | -2
UML Diagrams for SRS Document | Documentation | Sherley | 1 | 1 | Done
Research on TSP | Preparation | Aryanil | 1 | 1 | Done
UML Diagrams for SRS Document | Documentation | Akshitha | 1 | 1 | Done
Initialise Codebase | Development | Aviral | 1 | 1 | Done | 0
Geocoding | Development | Aviral | 3 | 2.5 | Done | 0.5
Week 6 (February 19 - February 25)
Team Meeting | Coordination | Aviral | 5 | 4 | Done | 1
Boiler Plate for VROOM implementation | Development | Aryanil | 5 |  | Ongoing | 5
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 0.5 | 0.5 | Done | 0