## Status
TEAM NUMBER | 28 |  |  | Note that all time values are rounded off to the nearest 30 minutes (half an hour)
PROJECT NAME | Fleet Management
CLIENT | Akhil
TEAM MEMBERS | Akshitha
Aryanil
Aviral
Satvik
Sherley
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Time Calculation Error
Week 1 (January 16 - January 21)
GIT Repository setup | Preparation | Aryanil | 1 | 0.5 | Done | 0.5
Client meeting | Coordination | Aviral | 5 | 4 | Done | 1
Research existing technology | Preparation | Sherley | 3 | 5 | Done | -2
Team Meeting | Coordination | Aviral | 5 | 4 | Done | 1
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5
Week 2 (January 22 - January 28)
Project Synopsis Writeup | Documentation | Sherley | 3 | 3.5 | Done | -0.5
Project Plan Document | Documentation | Akshitha | 4 | 4.5 | Done | -0.5
Software Requirement Specification | Documentation | Aviral | 3 | 2.5 | Done | 0.5
Team Meeting | Coordination | Aviral | 5 | 7 | Done | -2
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 0.5 | Done | 0.5
Week 3 (January 29 - February 4)
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Research TSP Algorithm for Routing | Preparation | Aryanil | 1 | 1 | Done | 0
VROOM | Preparation | Aryanil | 2 | 2 | Done | 0
Team Meeting | Coordination | Aviral | 7.5 | 7.5 | Done | 0
Update Status Tracker | Documentation | Satvik | 2 | 0.5 | Done | 1.5
Week 4 (February 5 - February 11)
Reasearch Grasshopper Optimisation Technique | Preparation | Aviral | 2 | 3 | Done | -1
Research on Data Acquisition | Preparation | Sherley | 3 | 3.5 | Done | -0.5
Data Importing Techniques | Preparation | Sherley | 2.5 |  | Done | 2.5
Research Heuristics Algorithms | Preparation | Aviral | 3 | 2.5 | Done | 0.5
Research on Geocoding | Preparation | Akshitha | 2 | 1.5 | Done | 0.5
Research on TSP (Contd.) | Preparation | Aryanil | 2 | 1 | Done | 1
Research on PgRouting | Preparation | Satvik | 2 | 2 | Done | 0
Update Status Tracker | Documentation | Satvik | 0.5 | 0.5 | Done | 0
Week 5 (February 12 - February 18)
Update SRS to match format | Documentation | Aviral | 5 | 7 | Done | -2
UML Diagrams for SRS Document | Documentation | Sherley | 1 | 1 | Done | 0
Research on TSP | Preparation | Aryanil | 1 | 1 | Done | 0
UML Diagrams for SRS Document | Documentation | Akshitha | 1 | 1 | Done | 0
Initialise Codebase | Development | Aviral | 1 | 1 | Done | 0
Geocoding | Development | Aviral | 3 | 2.5 | Done | 0.5
Week 6 (February 19 - February 25)
Team Meeting | Coordination | Aviral | 5 | 4 | Done | 1
Boiler Plate for VROOM implementation | Development | Aryanil |  |  | Discarded | 0
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 0.5 | 0.5 | Done | 0
Week 7 (February 26 - March 3)
Midsem break
Week 8 (March 4 - March 11)
VROOM implementation (Continuation) | Development | Satvik |  |  | Discarded | 0
Team Meet (Discuss Implementation Phase) | Coordination | Aviral | 2.5 | 2.5 | Done | 0
Client Meet (Discuss OSRM Data Storage) | Coordination | Aviral | 2.5 | 2 | Done | 0.5
Client meeting MoM Writeup | Documentation | Sherley | 1 | 1 | Done | 0
Team MoM Writeup | Documentation | Aryanil | 1 | 1 | Done | 0
Status tracker | Documentation | Aryanil | 0.5 | 0.5 | Done | 0
Code Function Blocks Implementation | Development | Aviral |  |  | Discarded | 0
Code Function Blocks Implementation | Development | Sherley |  |  | Discarded | 0
Code Function Blocks Implementation | Development | Akshita |  |  | Discarded | 0
Week 9 (March 12 - March 19)
Client Meet | Coordination | Aviral | 2.5 | 2.5 | Done | 0
Google APIs Market Research | Documentation | Sherley | 1 | 1.5 | Done | -0.5
Client Meet MoM | Documentation | Aviral | 1 | 1 | Done | 0
Design Document (Class Diagrams) | Documentation | Aryanil | 6 | 6 | Done | 0
Design Document (Sequence Diagrams) | Documentation | Sherley | 3 | 3 | Done | 0
Design Document (Design Rational) | Documentation | Aviral | 1 | 1 | Done | 0
Implement Website Home, About, Timeline, Demos Page | Interfaces | Aviral | 5 | 5.5 | Done | -0.5
Implement Website Navbar | Interfaces | Aviral | 1 | 0.5 | Done | 0.5
Implement Website Teams Page | Interfaces | Aryanil | 1 | 0.5 | Done | 0.5
Implement Website Geocode and Route pages | Interfaces | Akshitha | 1.5 | 1 | Done | 0.5
Route optimization(Many-to-one) | Development | Akshitha | 3 | 6 | Done | -3
Updated Project Synopsis Document | Documentation | Sherley | 1 | 1 | Done | 0
Updated SRS for Google API | Documentation | Sherley | 2 | 3 | Done | -1
Updated Project Plan Document | Documentation | Akshitha | 1 | 1 | Done | 0
Implementation of autocomplete feature in search functionalities | Development | Sherley | 3 | 4 | Done | -1
R1 Presentaion Deck | Documentation |  | 5 | 12 | Done | -7
Database setup | Development | Satvik | 2 |  | Delayed | 2
Login Page | Development | Satvik | 2 |  | Delayed | 2
Team MoM Writeup | Documentation | Satvik | 1 | 1 | Done | 0
Status tracker | Documentation | Satvik | 1 | 1 | Done | 0
Route optimization(Many-to-many) | Development | Akshitha | 2 | 4 | Done | -2
Redesigned Project Class Diagram and Sequence Diagrams | Design | Sherley | 2 | 3 | Done | -1
Added Readme for The repo | Documentation | Aryanil | 2 | 2 | Done | 0